## Tabelle1
Time spent on use cases
Project: turnie.re
TINF17B4
Use Case | Documentation | Coding | Testing | Warm-Up time | Total | FP
Time spent in Semester 3 (hours)
Login | 1 | 3.2 | 1.3 | 4 | 1.5 | 112.24
Register | 1 | 2.5 | 2 | 3 | 2.5 | 112.24
View Tournament | 0.2 | 16 | 6 |  | 22.2 | 109.48
List Tournaments | 0.5 | 13 |  |  | 13.5 | 109.48
Estimation for Semester 4 (hours)
TournamentCRUD | 3 | 20 | 5 | 3 | 25 | 143.52
UserCRUD | 4 | 14 | 8 | 1 | 25 | 141.68
MatchCRUD | 2 | 30 | 10 |  | 42 | 117.76
MatchBetting | 3 | 18 | 2 |  | 23 | 79.3
Statistics Page | 0.5 | 12 | 1 |  | 13.5 | 109.84
Time-FP-Evaluation
Semester 3
Use Case Time | 1: FP; 3.2: Time Total; 1.3: Time/FP
Login | 1: 112.24; 3.2: 1.5; 1.3: 0.013364
Register | 1: 112.24; 3.2: 2.5; 1.3: 0.022274
View Tournament | 1: 109.48; 3.2: 22.2; 1.3: 0.20278
List Tournaments | 1: 109.48; 3.2: 13.5; 1.3: 0.12331
Total Semester 3 | 1: 443.44; 3.2: 39.7; 1.3: 0.089527
Semester 4
Estimation | 1: FP; 3.2: Time (estimated)
TournamentCRUD | 1: 143.52; 3.2: 12.849
UserCRUD | 1: 141.68; 3.2: 12.6842
MatchCRUD | 1: 117.76; 3.2: 10.5427
MatchBetting | 1: 79.3; 3.2: 7.0995
Statistics Page | 1: 109.84; 3.2: 9.8337
Total Semester 4 | 1: 592.1; 3.2: 53.0091